## The portfolio
Public Investment Portfolio, PIMNIA
PIMNIA is a middle-income country that at the end of 2016 has a public investment portfolio comprising 28 projects (16 on-going and 12 new projects yet to be implemented). These projects belong to 5 economic sectors: agriculture, health, education, public works and transport, and water and sanitation. Details for each of the 28 projects comprising the overall PIP portfolio are included in the tab "The PIP portfolio"
The government has identified that the strategic planning priority for the country is improve transport connectivity and health outcomes.
The country has two fiscal rules: overall deficit cannot exceed 3.0% of GDP and public gross debt cannot exceed 50% of GDP. By the end of 2016, PIMNIA overall fiscal deficit is above the rule (-3.4% of GDP) while its gross debt is sligthly lower than the ceiling (48.5% of GDP).
The macrofiscal projection done by the macroeconomic department of the MoF are presented in the tab "Macro Var". These include some historic information and projections for the budget and MTFF period (2017-2020) as well as long-term projections for the whole economy.
The government expects to converge to the overall fiscal deficit ceiling of 3.0% by the end of the MTFF (2020), for which is will extremelly important to keep expenditures within the medium-term expenditure ceiling. In row 17 of tab "Macro Var", the nominal ceiling for capital expenditures is presented.
At the end of 2016, the ministry of finance is in the process of prioritizing and selecting infrastructure projects to be included in the 2017 budget and its medium-term expenditure framework (2018-2020).
The task
The government need to select which of the 28 projects of its portfolio can be included in the budget without exceeding the capital expenditure ceiling (row 17 in tab "Macro Var")
For that, government officials will input in tab "The PIP portfolio" column AP, a YES/NO answer (using a drop-down menu). With YES for selecting the project for inclusion in the budget, and NO for excluding it.
To check if projects selected are fiscally affordable, meaning they fit within the fiscal space asigned for capital spending, look at tab "Simulations of 2017 MTEF".
This tab automatically calculate whether the set of projects selected fit within the capital expenditure ceiling (red horizontal bar in charts).
Please discuss in your group:,
Which are the projects that should be selected for inclusion in the budget in 2017-2020?
What are reasons behing this selection?

## Macro Var
COUNTRY PARAMETERS | [51 empty] | 10 | 1
| Year | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062
Account DOM
Nominal GDP in national currency (billion) |  | 2117.3643 | 2392.0251 | 2736.2176 | 3051.9751 | 3546.4108 | 4016.6772 | 4525.1585 | 5055.2948 | 5627.9266 | 6218.8589 | 6822.0882 | 7422.432 | 8053.3387 | 8721.7658 | 9436.9506 | 10144.7219 | 10895.4314 | 11603.6344 | 12357.8706 | 13161.1322 | 14016.6058 | 14927.6852 | 15897.9848 | 16931.3538 | 18031.8918 | 19203.9647 | 20452.2224 | 21781.6169 | 23197.422 | 24705.2544
Real GDP in national currency (billion) |  | 1602.1209 | 1684.8975 | 1787.4385 | 1844.3475 | 1938.6039 | 2006.1505 | 2076.2987 | 2149.1926 | 2226.363 | 2316.976 | 2409.8867 | 2505.0772 | 2600.2702 | 2697.7803 | 2798.4075 | 2901.3889 | 3006.4192 | 3111.6438 | 3220.5514 | 3333.2707 | 3449.9351 | 3570.6829 | 3695.6568 | 3825.0048 | 3958.8799 | 4097.4407 | 4240.8512 | 4389.2809 | 4542.9058 | 4701.9075
GDP deflator (units) |  | 132.1601 | 141.9686 | 153.0804 | 165.4772 | 182.9363 | 200.2181 | 217.9435 | 235.2183 | 252.7857 | 268.4041 | 283.0875 | 296.2955 | 309.7116 | 323.2941 | 337.2257 | 349.6505 | 362.4056 | 372.9101 | 383.7191 | 394.8414 | 406.2861 | 418.0625 | 430.1802 | 442.6492 | 455.4796 | 468.6819 | 482.2669 | 496.2457 | 510.6296 | 525.4305
NER DOM/Relevant FX |  | 205.6648 | 236.386 | 293.8789 | 326.2961 | 389.1568 | 409.3671 | 434.1047 | 457.981 | 483.2813 | 509.6626 | 509.6626 | 509.6626 | 509.6626 | 500 | 480 | 479 | 468 | 462 | 445 | 430 | 412 | 385 | 375 | 365 | 350 | 350 | 350 | 350 | 350 | 350
Primary Net Lending/Borrowing - Primary Balance (billion) |  | 25.2322 | 18.73 | 23.291 | -41.3238 | -42.5569 | -52.2168 | -49.7767 | -50.5529 | -45.0234 | -43.532 | -34.1104 | -37.1122 | -40.2667 | -43.6088 | -47.1848 | -50.7236 | -54.4772 | -58.0182 | -61.7894 | -65.8057 | -70.083 | -74.6384 | -79.4899 | -84.6568 | -90.1595 | -96.0198 | -102.2611 | -108.9081 | -115.9871 | -123.5263
Net Lending/Borrowing - Overall Balance (billion) |  | -45.2036 | -49.6977 | -50.2988 | -102.7203 | -113.4851 | -132.5503 | -140.2799 | -151.6588 | -157.5819 | -167.9092 | -170.5522 | -185.5608 | -201.3335 | -218.0441 | -235.9238 | -253.618 | -272.3858 | -290.0909 | -308.9468 | -329.0283 | -350.4151 | -373.1921 | -397.4496 | -423.2838 | -450.7973 | -480.0991 | -511.3056 | -544.5404 | -579.9355 | -617.6314
Cash balance (billion) |  | -37 | -25 | -42 | -89 | -113.4851 | -132.5503 | -140.2799 | -151.6588 | -157.5819 | -167.9092 | -170.5522 | -185.5608 | -201.3335 | -218.0441 | -235.9238 | -253.618 | -272.3858 | -290.0909 | -308.9468 | -329.0283 | -350.4151 | -373.1921 | -397.4496 | -423.2838 | -450.7973 | -480.0991 | -511.3056 | -544.5404 | -579.9355 | -617.6314
Government gross debt projections, DSA (billion) |  | 1079.8558 | 1188.5858 | 1351.8768 | 1480.553 | 1523.11 | 1575.3268 | 1625.1035 | 1675.6565 | 1720.6799 | 1764.2119 | 1798.3223 | 1835.4345 | 1875.7012 | 1919.31 | 1966.4948 | 2017.2184 | 2071.6955 | 2129.7137 | 2191.5031 | 2257.3087 | 2327.3917 | 2402.0302 | 2481.5201 | 2566.1769 | 2656.3363 | 2752.3561 | 2854.6173 | 2963.5253 | 3079.5125 | 3203.0387
Of which debt on PPPs, including PPPs in pipeline (billions) |  | 0 | 31.3333 | 75 | 124.6667 | 132 | 131.7676 | 130.4807 | 128.0695 | 124.4063 | 130.4644 | 125.3537 | 119.1156 | 111.6356 | 102.8516 | 92.691 | 91.9814 | 79.642 | 65.6788 | 49.9959 | 32.4065 | 13.3817 | 12.2227 | 11.0168 | 9.7597 | 8.4781 | 7.0749 | 5.5387 | 3.8569 | 2.0157 | 0
Government Revenue (billion) |  | 639.444 | 741.5278 | 854.2471 | 936.9564 | 1063.9232 | 1196.9698 | 1348.4972 | 1506.4779 | 1677.1221 | 1853.22 | 2114.8474 | 2300.9539 | 2496.535 | 2703.7474 | 2925.4547 | 3144.8638 | 3377.5837 | 3597.1267 | 3830.9399 | 4079.951 | 4345.1478 | 4627.5824 | 4928.3753 | 5248.7197 | 5589.8864 | 5953.2291 | 6340.189 | 6752.3012 | 7191.2008 | 7658.6289
Governemnt Total Expenditures (billion) |  | 684.6476 | 791.2255 | 904.5459 | 1039.6767 | 1177.4084 | 1329.5202 | 1488.7771 | 1658.1367 | 1834.7041 | 2021.1292 | 2285.3996 | 2486.5147 | 2697.8685 | 2921.7916 | 3161.3785 | 3398.4819 | 3649.9695 | 3887.2175 | 4139.8867 | 4408.9793 | 4695.563 | 5000.7745 | 5325.8249 | 5672.0035 | 6040.6837 | 6433.3282 | 6851.4945 | 7296.8417 | 7771.1364 | 8276.2602
Government Interest (billion) |  | 42.3473 | 47.8405 | 54.7244 | 61.3965 | 70.9282 | 80.3335 | 90.5032 | 101.1059 | 112.5585 | 124.3772 | 136.4418 | 148.4486 | 161.0668 | 174.4353 | 188.739 | 202.8944 | 217.9086 | 232.0727 | 247.1574 | 263.2226 | 280.3321 | 298.5537 | 317.9597 | 338.6271 | 360.6378 | 384.0793 | 409.0444 | 435.6323 | 463.9484 | 494.1051
Government current expenditures, excluding interest (billions) |  | 515.2585 | 599.8635 | 658.2863 | 734.0802 | 851.1386 | 964.0025 | 1086.7168 | 1214.7874 | 1353.235 | 1496.2575 | 1642.4177 | 1788.0639 | 1941.2573 | 2103.6899 | 2277.608 | 2449.9503 | 2632.881 | 2805.7588 | 2989.9868 | 3186.3101 | 3395.5228 | 3618.4709 | 3856.0562 | 4109.2396 | 4379.0449 | 4666.5634 | 4972.9579 | 5299.4674 | 5647.4124 | 6018.2
Government capital expenditures (billions) Nominal ceiling MTFF |  | 127.0419 | 143.5215 | 191.5352 | 244.2 | 255.3416 | 285.1841 | 311.5572 | 342.2435 | 434.2674 | 475.1208 | 506.5401 | 550.0022 | 595.5444 | 643.6663 | 695.0314 | 745.6371 | 799.1799 | 849.386 | 902.7425 | 959.4465 | 1019.7081 | 1083.7499 | 1151.809 | 1224.1369 | 1301.001 | 1382.6855 | 1469.4922 | 1561.7419 | 1659.7755 | 1763.9552
Of which capital expendtures on PPPs (billions) |  | 0 | 31.3333 | 43.6667 | 49.6667 | 7.3333 | 0 | 0 | 0
Rates of growth
Nominal GDP in national currency |  |  | 12.97% | 14.39% | 11.54% | 16.2% | 13.26% | 12.66% | 11.72% | 11.33% | 10.5% | 9.7% | 8.8% | 8.5% | 8.3% | 8.2% | 7.5% | 7.4% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5% | 6.5%
Real GDP in national currency |  |  | 5.167% | 6.086% | 3.184% | 5.111% | 3.484% | 3.497% | 3.511% | 3.591% | 4.07% | 4.01% | 3.95% | 3.8% | 3.75% | 3.73% | 3.68% | 3.62% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5%
GDP deflator |  |  | 7.422% | 7.827% | 8.098% | 10.55% | 9.447% | 8.853% | 7.926% | 7.469% | 6.179% | 5.471% | 4.666% | 4.528% | 4.386% | 4.309% | 3.684% | 3.648% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899% | 2.899%
NER |  |  | 14.94% | 24.32% | 11.03% | 19.26% | 5.193% | 6.043% | 5.5% | 5.524% | 5.459% | 0% | 0% | 0% | -1.896% | -4% | -0.2083% | -2.296% | -1.282% | -3.68% | -3.371% | -4.186% | -6.553% | -2.597% | -2.667% | -4.11% | 0% | 0% | 0% | 0% | 0%
% GDP
Primary Net Lending/Borrowing - Primary Balance (billion) |  | 1.1917 | 0.78302 | 0.85121 | -1.354 | -1.2 | -1.3 | -1.1 | -1 | -0.8 | -0.7 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
Net Lending/Borrowing - Overall Balance (billion) |  | -2.1349 | -2.0776 | -1.8383 | -3.3657 | -3.2 | -3.3 | -3.1 | -3 | -2.8 | -2.7 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5
Cash balance (billion) |  | -1.7475 | -1.0451 | -1.535 | -2.9161 | -3.2 | -3.3 | -3.1 | -3 | -2.8 | -2.7 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5
Government gross debt projections, DSA (billion) |  | 51 | 49.6895 | 49.4068 | 48.5113 | 42.9479 | 39.2197 | 35.9126 | 33.1466 | 30.574 | 28.3687 | 26.3603 | 24.7282 | 23.291 | 22.006 | 20.8382 | 19.8844 | 19.0144 | 18.3539 | 17.7337 | 17.1513 | 16.6045 | 16.0911 | 15.609 | 15.1564 | 14.7313 | 14.3322 | 13.9575 | 13.6056 | 13.2752 | 12.965
Of which debt on PPPs, including PPPs in pipeline (billions) |  | 0 | 1.3099 | 2.741 | 4.0848 | 3.7221 | 3.2805 | 2.8835 | 2.5334 | 2.2105 | 2.0979 | 1.8375 | 1.6048 | 1.3862 | 1.1793 | 0.98221 | 0.90669 | 0.73097 | 0.56602 | 0.40457 | 0.24623 | 0.09547 | 0.081879 | 0.069297 | 0.057643 | 0.047017 | 0.036841 | 0.027081 | 0.017707 | 0.0086895 | 0
Government Revenue (billion) |  | 30.2 | 31 | 31.22 | 30.7 | 30 | 29.8 | 29.8 | 29.8 | 29.8 | 29.8 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
Governemnt Total Expenditures (billion) |  | 32.3349 | 33.0776 | 33.0583 | 34.0657 | 33.2 | 33.1 | 32.9 | 32.8 | 32.6 | 32.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
Government Interest (billion) |  | 2 | 2 | 2 | 2.0117 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Government current expenditures, excluding interest (billions) |  | 24.3349 | 25.0776 | 24.0583 | 24.0526 | 24 | 24 | 24.015 | 24.03 | 24.045 | 24.06 | 24.075 | 24.09 | 24.105 | 24.12 | 24.135 | 24.15 | 24.165 | 24.18 | 24.195 | 24.21 | 24.225 | 24.24 | 24.255 | 24.27 | 24.285 | 24.3 | 24.315 | 24.33 | 24.345 | 24.36
Government capital expenditures (billions) Nominal ceiling MTFF |  | 6 | 6 | 7 | 8.0014 | 7.2 | 7.1 | 6.885 | 6.77 | 7.7163 | 7.64 | 7.425 | 7.41 | 7.395 | 7.38 | 7.365 | 7.35 | 7.335 | 7.32 | 7.305 | 7.29 | 7.275 | 7.26 | 7.245 | 7.23 | 7.215 | 7.2 | 7.185 | 7.17 | 7.155 | 7.14
Of which capital expendtures on PPPs (billions) |  | 0 | 1.3099 | 1.5959 | 1.6274 | 0.20678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Government PPPs capital expenditures in pipeline (billions) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Issues for the exercise
Country national fiscal rules
Deficit < 3.0 % GDP |  |  |  |  | Starting point above the limit of the rule
Gross Debt < 50% GDP |  |  |  |  | Starting point close to the limit
[6 empty] | Next budget | MTBF | MTBF | MTBF | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term | long-term
Revenues (% GDP) |  | 30.2 | 31 | 31.22 | 30.7 | 30 | 29.8 | 29.8 | 29.8 | 29.8 | 29.8 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
Expenditures (% GDP) |  | 32.3349 | 33.0776 | 33.0583 | 34.0657 | 33.2 | 33.1 | 32.9 | 32.8 | 32.6 | 32.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
Of which: current expenditures (residual) |  |  |  |  | 26.0657
Of which: capital expenditures (assumption % GDP at the initial point) |  |  |  |  | 8
Deficit (% GDP) |  | -2.1349 | -2.0776 | -1.8383 | -3.3657 | -3.2 | -3.3 | -3.1 | -3 | -2.8 | -2.7 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5
Gross Debt (% GDP) |  | 51 | 49.6895 | 49.4068 | 48.5113 | 42.9479 | 39.2197 | 35.9126 | 33.1466 | 30.574 | 28.3687 | 26.3603 | 24.7282 | 23.291 | 22.006 | 20.8382 | 19.8844 | 19.0144 | 18.3539 | 17.7337 | 17.1513 | 16.6045 | 16.0911 | 15.609 | 15.1564 | 14.7313 | 14.3322 | 13.9575 | 13.6056 | 13.2752 | 12.965
PPP portfolio |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Capital spending | PFRAM portfolio (NANFA) | 0 | 31.3333 | 43.6667 | 49.6667 | 7.3333 | 0 | 0 | 0
| P1 | 0 | 0 | 0 | 0 | 12.846 | 12.846 | 12.846 | 0
| P2 | 0 | 31.3333 | 31.3333 | 42.3333 | 0 | 0 | 0 | 0
| P3 | 0 | 7.85 | 7.85 | 0 | 0 | 0 | 0 | 0
| P4 | 0 | 0 | 12.3333 | 7.3333 | 7.3333 | 0 | 0 | 0
| P5 | 3.75 | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0
| P6 | 0 | 0 | 0 | 0 | 0 | 30 | 39 | 0
| P7 | 0 | 0 | 0 | 3.25 | 3.25 | 0 | 0 | 0
| P8 | 0 | 0 | 0 | 0 | 153.3333 | 153.3333 | 153.3333 | 0
| % of capital sp. | 0% | 21.83% | 22.8% | 20.34% | 2.872% | 0% | 0% | 0%
Debt | PFRAM portfolio | 0 | 31.3333 | 75 | 124.6667 | 132 | 131.7676 | 130.4807 | 128.0695 | 124.4063 | 130.4644 | 125.3537 | 119.1156 | 111.6356 | 102.8516 | 92.691 | 91.9814 | 79.642 | 65.6788 | 49.9959 | 32.4065 | 13.3817 | 12.2227 | 11.0168 | 9.7597 | 8.4781 | 7.0749 | 5.5387 | 3.8569 | 2.0157 | 0
| P1 | 0 | 0 | 0 | 0 | 12.846 | 25.692 | 38.538 | 38.3715 | 37.7948 | 36.7976 | 35.3455 | 33.4118 | 30.9289 | 27.8214 | 24.0001 | 19.405 | 13.9278 | 7.503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P2 | 0 | 31.3333 | 62.6667 | 105 | 105 | 104.7893 | 103.6823 | 101.6184 | 98.495 | 105.3105 | 101.0288 | 95.6984 | 89.2122 | 81.4553 | 72.2929 | 72.6699 | 61.4508 | 48.6762 | 34.1874 | 17.8106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P3 | 0 | 7.85 | 15.7 | 15.5787 | 15.2237 | 14.6082 | 13.6943 | 12.4505 | 10.8322 | 8.8173 | 6.3682 | 3.4494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P4 | 0 | 0 | 12.3333 | 19.6667 | 27 | 26.9783 | 26.7985 | 26.4511 | 25.9113 | 25.154 | 24.3249 | 23.4171 | 22.4234 | 21.3964 | 20.3981 | 19.3115 | 18.1912 | 17.0026 | 15.8085 | 14.5958 | 13.3817 | 12.2227 | 11.0168 | 9.7597 | 8.4781 | 7.0749 | 5.5387 | 3.8569 | 2.0157 | 0
| P5 | 3.75 | 7.5 | 11.25 | 15 | 14.4 | 13.8 | 13.2 | 12.6 | 12 | 11.4 | 10.8 | 10.2 | 9.6 | 9 | 8.4 | 7.8 | 7.2 | 6.6 | 6 | 5.4 | 4.8 | 4.2 | 3.6 | 3 | 2.4 | 1.8 | 1.2 | 0.6 | 0 | 0
| P6 | 0 | 0 | 0 | 0 | 0 | 30 | 69 | 63.4286 | 57.8571 | 52.2857 | 46.7143 | 41.1429 | 35.5714 | 30 | 33.4286 | 27.8571 | 22.2857 | 16.7143 | 11.1429 | 5.5714 | 1.4552e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P7 | 0 | 0 | 0 | 3.25 | 6.5 | 5.997 | 5.4265 | 4.7795 | 4.0433 | 3.2102 | 2.2679 | 1.2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P8 | 0 | 0 | 0 | 0 | 153.3333 | 306.6667 | 460 | 440 | 420 | 400 | 380 | 360 | 340 | 320 | 300 | 280 | 260 | 240 | 220 | 200 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 20 | 0
| % of gross debt | 0% | 2.636% | 5.548% | 8.42% | 8.666% | 8.364% | 8.029% | 7.643% | 7.23% | 7.395% | 6.971% | 6.49% | 5.952% | 5.359% | 4.714% | 4.56% | 3.844% | 3.084% | 2.281% | 1.436% | 0.575% | 0.5088% | 0.444% | 0.3803% | 0.3192% | 0.257% | 0.194% | 0.1301% | 0.06546% | 0%
Some general calculations
interest | fixed |  |  |  | 2.0117 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[5 empty] | 61.3965 | 70.9282 | 80.3335 | 90.5032 | 101.1059 | 112.5585 | 124.3772 | 136.4418 | 148.4486 | 161.0668 | 174.4353 | 188.739 | 202.8944 | 217.9086 | 232.0727 | 247.1574 | 263.2226 | 280.3321 | 298.5537 | 317.9597 | 338.6271 | 360.6378 | 384.0793 | 409.0444 | 435.6323 | 463.9484 | 494.1051
deficit | %GDP |  |  |  | -3.3657 | -3.2 | -3.3 | -3.1 | -3 | -2.8 | -2.7 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5
| Nominal |  |  |  | -102.7203 | -113.4851 | -132.5503 | -140.2799 | -151.6588 | -157.5819 | -167.9092 | -170.5522 | -185.5608 | -201.3335 | -218.0441 | -235.9238 | -253.618 | -272.3858 | -290.0909 | -308.9468 | -329.0283 | -350.4151 | -373.1921 | -397.4496 | -423.2838 | -450.7973 | -480.0991 | -511.3056 | -544.5404 | -579.9355 | -617.6314
primary deficit |  |  |  |  | -1.354 | -1.2 | -1.3 | -1.1 | -1 | -0.8 | -0.7 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5
[5 empty] | -41.3238 | -42.5569 | -52.2168 | -49.7767 | -50.5529 | -45.0234 | -43.532 | -34.1104 | -37.1122 | -40.2667 | -43.6088 | -47.1848 | -50.7236 | -54.4772 | -58.0182 | -61.7894 | -65.8057 | -70.083 | -74.6384 | -79.4899 | -84.6568 | -90.1595 | -96.0198 | -102.2611 | -108.9081 | -115.9871 | -123.5263
revenues |  |  |  |  | 30.7 | 30 | 29.8 | 29.8 | 29.8 | 29.8 | 29.8 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
[5 empty] | 936.9564 | 1063.9232 | 1196.9698 | 1348.4972 | 1506.4779 | 1677.1221 | 1853.22 | 2114.8474 | 2300.9539 | 2496.535 | 2703.7474 | 2925.4547 | 3144.8638 | 3377.5837 | 3597.1267 | 3830.9399 | 4079.951 | 4345.1478 | 4627.5824 | 4928.3753 | 5248.7197 | 5589.8864 | 5953.2291 | 6340.189 | 6752.3012 | 7191.2008 | 7658.6289
total expenditures |  |  |  |  | 34.0657 | 33.2 | 33.1 | 32.9 | 32.8 | 32.6 | 32.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5 | 33.5
[5 empty] | 1039.6767 | 1177.4084 | 1329.5202 | 1488.7771 | 1658.1367 | 1834.7041 | 2021.1292 | 2285.3996 | 2486.5147 | 2697.8685 | 2921.7916 | 3161.3785 | 3398.4819 | 3649.9695 | 3887.2175 | 4139.8867 | 4408.9793 | 4695.563 | 5000.7745 | 5325.8249 | 5672.0035 | 6040.6837 | 6433.3282 | 6851.4945 | 7296.8417 | 7771.1364 | 8276.2602
captital expenditures | residual |  |  |  | 8 | 7.2 | 7.1 | 6.885 | 6.77 | 6.555 | 6.44 | 7.425 | 7.41 | 7.395 | 7.38 | 7.365 | 7.35 | 7.335 | 7.32 | 7.305 | 7.29 | 7.275 | 7.26 | 7.245 | 7.23 | 7.215 | 7.2 | 7.185 | 7.17 | 7.155 | 7.14
| Nominal ceiling |  |  |  | 244.158 | 255.3416 | 285.1841 | 311.5572 | 342.2435 | 368.9106 | 400.4945 | 506.5401 | 550.0022 | 595.5444 | 643.6663 | 695.0314 | 745.6371 | 799.1799 | 849.386 | 902.7425 | 959.4465 | 1019.7081 | 1083.7499 | 1151.809 | 1224.1369 | 1301.001 | 1382.6855 | 1469.4922 | 1561.7419 | 1659.7755 | 1763.9552
Current (excluding interest) | fixed, increasing (population) |  |  |  | 24.054 | 24 | 24 | 24.015 | 24.03 | 24.045 | 24.06 | 24.075 | 24.09 | 24.105 | 24.12 | 24.135 | 24.15 | 24.165 | 24.18 | 24.195 | 24.21 | 24.225 | 24.24 | 24.255 | 24.27 | 24.285 | 24.3 | 24.315 | 24.33 | 24.345 | 24.36
[5 empty] | 734.1222 | 851.1386 | 964.0025 | 1086.7168 | 1214.7874 | 1353.235 | 1496.2575 | 1642.4177 | 1788.0639 | 1941.2573 | 2103.6899 | 2277.608 | 2449.9503 | 2632.881 | 2805.7588 | 2989.9868 | 3186.3101 | 3395.5228 | 3618.4709 | 3856.0562 | 4109.2396 | 4379.0449 | 4666.5634 | 4972.9579 | 5299.4674 | 5647.4124 | 6018.2
Gross debt |  |  |  |  | 48.5113 | 42.9479 | 39.2197 | 35.9126 | 33.1466 | 30.574 | 28.3687 | 26.3603 | 24.7282 | 23.291 | 22.006 | 20.8382 | 19.8844 | 19.0144 | 18.3539 | 17.7337 | 17.1513 | 16.6045 | 16.0911 | 15.609 | 15.1564 | 14.7313 | 14.3322 | 13.9575 | 13.6056 | 13.2752 | 12.965
[5 empty] | 1480.553 | 1523.11 | 1575.3268 | 1625.1035 | 1675.6565 | 1720.6799 | 1764.2119 | 1798.3223 | 1835.4345 | 1875.7012 | 1919.31 | 1966.4948 | 2017.2184 | 2071.6955 | 2129.7137 | 2191.5031 | 2257.3087 | 2327.3917 | 2402.0302 | 2481.5201 | 2566.1769 | 2656.3363 | 2752.3561 | 2854.6173 | 2963.5253 | 3079.5125 | 3203.0387
Note on F2: Rial, Isabel: We assumed that we are in last quarter 2016
Note on F58: Rial, Isabel: This should be the total value of the investment of ongoing projects in the portfolio
Note on G58: Rial, Isabel: and here it would be what we plan to invest in next budget
Continue >>
Select the first year cell where you
want to paste the data, then click
on "paste" button to the left.
PASTE
Continue >>
Select the first year cell where you
want to paste the data, then click
on "paste" button to the left.
PASTE

## The PIP portfolio
[48 empty] | 79.0095 | 35.2236 | 52.4492 | 51.0636 | 52.9642 | 48.6867 | 37.4738
[10 empty] | Project Strategic Alignment |  |  |  | Total Project Cost |  |  |  | Project Financing Structure |  |  |  | Project Execution Prior to 2016 |  |  |  |  | Executed | Planned | [5 empty] | Operation and Maintenance |  |  |  |  | Debt Stock
N | Project Title | Sector | Implementing Agency | GOP/ PPP | Feasibility Study | Appraisal indicator | Value | Project Status | Implementation Percentage | National Plan Objective | Project Outcomes | Project Outputs | Project Activities | Original Cost (LC$) | Updated Cost (LC$) | Increase vs. Original Cost | % GDP | GoP Revenue | Dev. Partner | Market Loan | Grant | Total | GoP Revenue | Dev. Partner | Market Loan | Grant | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer Years | 2017 | 2018 | 2019 | 2020 | Include in 2017 Budget | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer | Group1 | Group2 | Group3 | Group4 | Group5 | Group6
1 | Cotton Production Improvement | Agriculture | Ministry of Agriculture | GOP | No | NPV | 114.3 | Ongoing | Above 90% | Improve access to high quality seeds and planting materials | Increased efficiency in processing cotton planting seed | a) Acquisition of land b) Construction of seed processing structures c) Procurement and installation of specialized machinery for processing cotton planting seed | Procure land. Construct Perimeter Fence, Guard House, Ablution Block, Front Office, Ginning Hall, Delinting Hall, Seed Bagging area, Raw Cotton stores, cyclone dust chambers, Un-processed cottonseed store, Processed cottonseed store, Bale shed, Multi-purpose hall, Offices, Dinning hall, kitchen, canteen, Main store, Workshop, Pit latrines with showers, Power House, Pump House, borehole, overhead water tank, External works (i.e. drive ways, landscaping, drainage), Electrical and mechanical installations. Procure and install ginning equipment, seed dryer, seed delinter, gravity and size seed graders, seed treater and bagging machine, weighbridge. Relocate and install some of the existing seed processing machinery to the site. | 33 | 35 | 6.061% | 1.147% | 11 | 24 | 0 | 0 | 30 | 6 | 24 | 0 | 0 | 3.4 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Construction of Pimnia National University Expansion | Education | Ministry of Education | GOP | No | PVC/PVBenef | 1.9 | Ongoing | 41%-50% | Expand and improve school infrastructure for all levels, including water supply infrastructure, sanitation and hand-washing facilities, school physical education and community facilities | Improved facilities | 35 hectars of land to be acquired by swapping with National Forest Authority, 3,000 Hectares of forest property of the University. Construct 1 ICT block, 1 Library Block, 2 lecture blocks and 2 Administration building and a 2000 capacity Library building. | Completion of Land purchase and title documentation for lands and constructions in plan, Complete Master Plan Development, Complete Building Plans, Drawings and BOQ for New Library, Multifunctional Material Testing Laboratory Directorate of ICT Building. | 15.6812 | 17.5 | 11.6% | 0.5734% | 13.5 | 4 | 0 | 0 | 6.7 | 2.7 | 4 | 0 | 0 | 6 | 3 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Education Infrastructure Rehabilitation | Education | Ministry of Education | GOP | Yes | PVC/PVBenef | 0.5 | New | 0% | Rehabilitate, expand and equip existing facilities at primary, secondary and post-secondary levels. | Rehabilitate classrooms, science laboratories, administration blocks, houses, libraries and multi-purpose halls. Provide furniture for classrooms, laboratories and staff rooms Provide instructional materials for all subjects | Carry out rehabilitation of the following buildings: classrooms, science laboratories, administration blocks, tutors houses, libraries and multi-purpose halls. Provide furniture for classrooms, laboratories and staff rooms Provide instructional materials for all subjects | Carry out rehabilitation of the following buildings: classrooms, science laboratories, administration blocks, tutors houses, libraries and multi-purpose halls. Provide furniture for classrooms, laboratories and staff rooms Provide instructional materials for all subjects | 32.12 | 32.12 | 0% | 1.052% | 1.24 | 10 | 0 | 20.88 | 0 | 0 | 0 | 0 | 0 | 0 | 12.1 | 10.88 | 9.14 | 0 | 0 | 0 | 0.3212 | 0.35154 | 0.38267 | 0.413 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
4 | High Performance Sport Training Centre. | Education | Ministry of Education | GOP | No | NA | 0 | New | 0% | Expand and improve school infrastructure for all levels, including water supply infrastructure, sanitation and hand-washing facilities, school physical education and community facilities | to provide a condusive environment for sports training and performance | 1) sports hostles constructed, 2) athletics track constructed, 3) artifical turf fields, 4) jogging track, 5)fencing and site roads constructed | 1) needs assesment, 2) designs, 3) staff recruitment, 4)coordination activities i.e site meetings, 5)monitoring and supervision. 6) environmnet impact assesment , 7) benchmarking activities , 8) construction of the facility , 9) Land acquisition and surveys , preliminaery infastructure constructed | 25.53 | 25.53 | 0% | 0.8365% | 13.53 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.53 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0
5 | Projecta University Infrastructure Development | Education | Ministry of Education | GOP | No | PVC/PVBenef | 2.1 | Ongoing | 61%-70% | Rehabilitate, expand and equip existing facilities at primary, secondary and post-secondary levels. | To create a conducive teaching and learning environment for nurturing students at the University. To enhance knowledge transformation and utilisation of research and innovations | Construction of lecture blocks, sports and recreation centre's developed and renovation of hostels | Preparation of bid documents and specifications for procurement of contractors and supplies, advertisement and evaluation of bids and award of Contract/tender for works and supplies | 19.4615 | 24 | 23.32% | 0.7864% | 19 | 5 | 0 | 0 | 17 | 12 | 5 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Social University Infrastructure Development | Education | Ministry of Education | GOP | No | PVC/PVBenef | 2 | New | 0% | Rehabilitate, expand and equip existing facilities at primary, secondary and post-secondary levels. | Fully functional University with all the basic infrastructure and social amenities in place | Construction of laboratories, workshops, library, administration block, dining block, lecture blocks, internal roads, drainage, security lighting | Construction of administrative, learning and support infrastructure Procure machinery, equipment, transport, Teaching and Learning Materials. Provide security to persons and property | 53.6 | 53.6 | 0% | 1.756% | 3.6 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 11.78 | 18 | 10.22 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pimnia Heart Institute Project | Health | Ministry of Health | GOP | No | PVC/PVBenef | 4.5 | Ongoing | Above 90% | Develop Health infrastructure, equipment and maintenance | Increased accessibility to heart services, a population well sensitised about heart diseases, a self reliance centre of excellence | Rehabilitation of buildings, relevant equipment procured (medical, furniture, transport and mechinery). Construction od additional square meters in wards and medical buildings | To improve the infrastructure and services of the institute to provide convinient and affordable heart treatment to the local population and the region. Undertake necessary capital expenditures in order to transform the institute into centre of excellence | 94.3333 | 126.5 | 34.1% | 4.145% | 31.5 | 95 | 0 | 0 | 82 | 2 | 80 | 0 | 0 | 15.5 | 10 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 80 | 86.3029 | 87.9216 | 89.2724 | 90.5023 | 91.9386 | 91.9386 | 95 | 0 | 6.3029 | 1.6187 | 1.3508 | 1.2299 | 1.4363 | 0 | 3.0614 | 1 | 1 | 1 | 1 | 1 | 0
8 | Rehabilitation of Neuro-surgery Referral Hospital | Health | Ministry of Health | GOP | No | PVC/PVBenef | 4 | New | 0% | Develop and upgrade health infrastructure. | Construction and rehabilitation of residential and non residential buildings. | Drug and sundries stores, Staff hostel, Surgical ward, Medical and eye wards rehabilitated. Road and walk ways rehabilitated | Construction of the main road to the hospital and walkways for easy access to wards and other treatment centres Construction of staff houses Rehabilitation of the drug and sundries stores, surgical ward, medical and eye wards | 16.2 | 16.2 | 0% | 0.5308% | 8.2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.3 | 6.2 | 0 | 0 | 0 | 2.7 | 0.162 | 0.1773 | 0.193 | 0.2083 | Yes | 0 | 0 | 1.1817 | 2.3781 | 2.3781 | 2.3781 | 2.3781 | 8 | 0 | 0 | 1.1817 | 1.1965 | 0 | 0 | 0 | 5.6219 | 0 | 1 | 1 | 0 | 0 | 0
9 | Rehabilitation of Pedriatic Referral Hospital of Pimnia | Health | Ministry of Health | GOP | No | PVC/PVBenef | 3.7 | New | 0% | Develop Health infrastructure, equipment and maintenance | Improvement of of healthservices and patient safety, Strenghthening mechanism for quality effective and efficient service delivery and motivative workforce. | There will be a construction of land titles, procuring of land titles, medical department to be renovated,labour suite and theatre renovated bathroom and tironet for paediatric ward constructed and drainage system overhauled. | Construction of the maternity ward ,procuring of the hospital land titles and renovation of labour and theatre suites. | 18.37 | 18.37 | 0% | 0.6019% | 6.37 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 6.2 | 10.37 | 0.9 | 0 | 0 | 0.1837 | 0.20105 | 0.21885 | 0.2362 | Yes | 0 | 0 | 0.14569 | 1.3421 | 3.1641 | 3.4227 | 3.4227 | 12 | 0 | 0 | 0.14569 | 1.1965 | 1.822 | 0.25853 | 0 | 8.5773 | 0 | 1 | 1 | 1 | 1 | 0
10 | Construction of Express Highway to National Airport | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 2879.5 | Ongoing | 61%-70% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Reduced travel time between the Metropolitan Area and National Airport through construction of an Expressway. | 16.8% of Civil works physical progress will be attained by end of end of 2020, 42 hectars of land acquired. | Construction of Expressway with 2x2x3.65m lanes and 2.1 median strip and 2.5m wide shoulder on both sides. | 170.625 | 180 | 5.495% | 5.898% | 40 | 70 | 70 | 0 | 105.5 | 3 | 59.7 | 42.8 | 0 | 17.5 | 15 | 13 | 12 | 8 | 9 | 0 | 5.4 | 5.9101 | 6.4334 | 6.9433 | Yes | 102.5 | 109.6161 | 112.0442 | 114.5529 | 116.6613 | 118.9594 | 122.294 | 140 | 0 | 7.1161 | 2.4281 | 2.5087 | 2.1084 | 2.298 | 3.3346 | 17.706 | 1 | 1 | 1 | 1 | 1 | 1
11 | Construction of Georgetown to Newport road | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 264.3 | Ongoing | 5%-10% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Reconnaissance, Sensitisation, survey and valuation data capture initiated Procurement of civil works contractor initiated | 16.8 Hectares of land acquired | Land and property compensation completed. Contractor procured | 78.2609 | 90 | 15% | 2.949% | 18 | 36 | 36 | 0 | 45 | 2.8 | 19 | 23.2 | 0 | 0 | 10 | 7.5 | 5 | 12 | 10.5 | 0 | 2.7 | 2.9551 | 3.2167 | 3.4716 | Yes | 42.2 | 42.2 | 43.8187 | 45.2661 | 46.1446 | 49.5916 | 53.482 | 72 | 0 | 0 | 1.6187 | 1.4473 | 0.8785 | 3.4471 | 3.8903 | 18.518 | 0 | 1 | 1 | 1 | 1 | 1
12 | Construction of Metropolitan Area Southern Bypass Phase 2 | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 945.9 | Ongoing | 31%-40% | Develop and maintain the roads to tourism, mining and agriculture producing areas | To release congestion and reduce travel time and vehicle operating costs for local and through traffic, and to protect city roads from damage by heavy commercial trucks and address specifc capacity constraints. | Traffic congestion reduced by diverting traffic away from the city centre | Hectares of land acquired,civil works carried out. | 74.9756 | 75 | 0.03253% | 2.457% | 15 | 30 | 30 | 0 | 45 | 0 | 27 | 18 | 0 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 2.25 | 2.4626 | 2.6806 | 2.893 | Yes | 45 | 51.0996 | 52.7183 | 53.6832 | 53.6832 | 53.6832 | 53.6832 | 60 | 0 | 6.0996 | 1.6187 | 0.96489 | 0 | 0 | 0 | 6.3168 | 1 | 1 | 1 | 0 | 0 | 0
13 | Construction of road from Paradise Valley to Great Falls National Park | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 298 | New | 0 | Develop and maintain the roads to tourism, mining and agriculture producing areas | An adequate and suitable road link between Paradise Valley and Great Falls National Park provided to increase tourism | Civil works and Supervision contractors procured by October 2020 Mobilisation will commence in Nov 2020 with 20% Advance Payment 10% of Civil works physical progress will be attained by end of June 2021 342 Hectares of land acquired | Feasibility study and Preliminary Engineering Design. Preparation and approval of the bidding documents for consultancy services for supervision of the design and build contract. Preparation and approval of the bidding documents for the design and build contract. Invitation of bids for design and build contract. Invitation of bids for supervision of the design and build works. Evaluation of bids and tender award. Contract signing | 293.24 | 293.24 | 0% | 9.608% | 30 | 263.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2 | 46 | 80 | 80 | 62.04 | 0 | 8.7972 | 9.6283 | 10.4807 | 11.3114 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263.24 | 0 | 0 | 0 | 0 | 0 | 0
14 | Construction of Rushing River Bridge | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 88.4 | New | 0 | Construct new and rehabilitate old bridges | To provide an adequate and suitable bridge link between approach road to facilitate iron production. | Selection of contractor and awarding of contract. Selection of supervision consultant. | Feasibility and preliminary engineering design. Selection of contractor and contract signing. | 78.811 | 78.811 | 0% | 2.582% | 7.913 | 35.449 | 35.449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 57 | 0 | 0 | 16.811 | 0 | 0 | 0 | 0 | Yes | 0 | 0 | 0 | 0.96489 | 10.9798 | 10.9798 | 10.9798 | 70.898 | 0 | 0 | 0 | 0.96489 | 10.0149 | 0 | 0 | 59.9182 | 0 | 0 | 1 | 1 | 0 | 0
15 | Design and construction of the New Grand River Bridge | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 1358.6 | Ongoing | 71%-80% | Construct new and rehabilitate old bridges | Second Grand River Bridge constructed. Traffic jams reduced. | 22% of Civil works physical progress will be attained by end of June 2019 1 Hectares of land acquired | Procurement of land. Construction and supervision of bridge works. | 223.7248 | 229.05 | 2.38% | 7.505% | 37.3 | 72.7 | 72.7 | 46.35 | 106.8 | 8.3 | 56 | 42.5 | 0 | 22 | 23.2 | 21.8 | 21.2 | 20.3 | 13.75 | 0 | 6.8715 | 7.5206 | 8.1864 | 8.8353 | Yes | 98.5 | 107.446 | 111.2015 | 115.4084 | 119.1332 | 124.9645 | 130.059 | 145.4 | 0 | 8.946 | 3.7555 | 4.2069 | 3.7248 | 5.8313 | 5.0945 | 15.341 | 1 | 1 | 1 | 1 | 1 | 1
16 | Expansion of North-South Metropolitan Area corridor. | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 587.44 | New | 0% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Improved mobility along the congested northen - southern corridors of Greater Metropolitan Area by diverting traffic from the existing road, Reduced travel time and cost, increased commercial viability of Greater Metropolitan Area, stimulated trade industry and agro-business and enhanced efficient passenger and freight operations. | Design review and supervision consultant procured, Civil works contractor procured, Project affected persons compensated/resettled, Right of way (ROW) acquired, The environment and social safeguards implementation plan prepared/implemented, 32km dual carriageway (2-4 lanes each direction, lane widths 3.7m) with 6 interchages (grade separeted junctions). | Procuring, engaging and supervising firms providing construction, construction supervision, land acquisition and compensation of affected properties along the project road. | 184.76 | 184.76 | 0% | 6.054% | 27 | 78.88 | 78.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 31.5 | 48 | 54.76 | 38.5 | 0 | 5.5428 | 6.0664 | 6.6035 | 7.1269 | Yes | 0 | 0 | 1.9425 | 8.0213 | 16.4548 | 32.1849 | 46.4495 | 157.76 | 0 | 0 | 1.9425 | 6.0788 | 8.4336 | 15.7301 | 14.2646 | 111.3105 | 0 | 1 | 1 | 1 | 1 | 1
17 | New Standard Gauge Railway Line | Public works and transport | National Railway Company | GOP | Yes | NPV | 19456.1 | Ongoing | 1% | Climate-proof existing and future transport infrastructure to ensure climate resilient transport systems | Lower transport cost, Regional trade enhanced and improved travel time | Detailed engineering designs for eastern route completed. Turnkey contracts for the western route signed and financing agreement signed. | Dermacation of ROW, Carry out detailed engineering designs for the eastern routes and negotiate the Turnkey contracts. | 230.4089 | 295.7029 | 28.34% | 9.689% | 64.95 | 87 | 93.7529 | 50 | 132.8 | 12.8 | 50 | 57.3 | 12.7 | 22 | 25 | 25.3 | 27.3 | 30 | 25.6 | 7.7029 | 8.8711 | 9.7091 | 10.5687 | 11.4064 | Yes | 107.3 | 116.246 | 120.2928 | 125.1752 | 129.9718 | 138.5894 | 148.0744 | 180.7529 | 0 | 8.946 | 4.0468 | 4.8823 | 4.7966 | 8.6177 | 9.485 | 32.6785 | 1 | 1 | 1 | 1 | 1 | 1
18 | Reconstruction of Francistown to border with Pimania road | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 1245 | Ongoing | 31%-40% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Improved transportation to tourism, mining and agriculture producing areas. | 155km of class 2 paved road reconstructed and upgraded to class 1 bitumen | Acquring land for right of way and reconstructing 155km of road. | 169.6774 | 173.2 | 2.076% | 5.675% | 80 | 68 | 0 | 25.2 | 126 | 32.8 | 68 | 0 | 25.2 | 18 | 15 | 8 | 6.2 | 0 | 0 | 0 | 5.196 | 5.6869 | 6.1903 | 6.681 | Yes | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Upgrading of Francistown to New Grand River Bridge | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 824.9 | Ongoing | 61%-70% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Francistown to New Grand River bridge (135km) upgraded to Class 1 paved standard. | 135 km of Class 2 road upgraded to Class 1 paved standard. | Construction and Supervision of works | 70.7965 | 80 | 13% | 2.621% | 40 | 40 | 0 | 0 | 50 | 10 | 40 | 0 | 0 | 16.5 | 6 | 6 | 1.5 | 0 | 0 | 0 | 2.4 | 2.6267 | 2.8593 | 3.0859 | Yes | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Upgrading of road from Georgetown to New Grand River bridge | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 759.6 | Ongoing | Above 90% | Develop and maintain the roads to tourism, mining and agriculture producing areas | Georgetown to New Grand River bridge (74km) upgraded to Class 1 paved standard. | 74km of Class 2 road upgraded to Class 1 paved standard. | Construction and Supervision of road works | 153.94 | 153.94 | 0% | 5.044% | 53.94 | 80 | 0 | 20 | 48.5 | 28.5 | 10 | 0 | 10 | 40 | 22 | 15.44 | 12.56 | 6.44 | 7 | 2 | 1.5394 | 1.6848 | 1.834 | 1.9794 | Yes | 10 | 26.2655 | 29.8267 | 32.8062 | 35.013 | 36.863 | 39.4565 | 80 | 0 | 16.2655 | 3.5612 | 2.9796 | 2.2068 | 1.8499 | 2.5936 | 40.5435 | 1 | 1 | 1 | 1 | 1 | 1
21 | Upgrading of road from Metropolitan Area to Francistown | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 45.9 | Ongoing | 45%-50% | Construct new and rehabilitate old bridges | Reduction in the cost and travel times for the movement of passengers and goods Reliable link between the centres of economic activity in the region. | Construction of 3 Bridges and 12 box culverts. | Completing the construction of 2 bridges and 6 culverts. | 7.3121 | 15.95 | 118.1% | 0.5226% | 15.95 | 0 | 0 | 0 | 10.6 | 10.6 | 0 | 0 | 0 | 2 | 3.35 | 0 | 0 | 0 | 0 | 0 | 0.4785 | 0.5237 | 0.57007 | 0.61525 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Upgrading of road from Newport to Paradise Valey | Public works and transport | Ministry of Public Works | GOP | Yes | NPV | 512.4 | New | 0 | Climate-proof existing and future transport infrastructure to ensure climate resilient transport systems | The economic feasibility study, preliminary engineering and detailed engineering designs were undertaken and finalized. | Design review and supervision consultant procured, Civil works contractor procured, Project affected persons compesated/resettled, Right of Way (ROW) acquired, The environment and social safeguards implementation plan prepared/implemented, 73km existing earthen /gravel roadway upgraded to paved asphaltic road. | i) Identify sources of project funding ii) On acquisition of project funding, procure, engage and supervise construction and supervision services. | 183.48 | 183.48 | 0% | 6.012% | 23.48 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 54.9 | 56 | 26.98 | 18.6 | 0 | 5.5044 | 6.0244 | 6.5577 | 7.0775 | Yes | 0 | 0 | 4.3706 | 14.965 | 24.8042 | 32.5543 | 39.4458 | 160 | 0 | 0 | 4.3706 | 10.5944 | 9.8392 | 7.7502 | 6.8915 | 120.5542 | 0 | 1 | 1 | 1 | 1 | 1
23 | Great Lake Sanitation Program | Water and Sanitation | National Water and Sewerage Corporation | GOP | Yes | PVC/PVBenef | 0.5 | Ongoing | 71%-80% | Increase sewerage connections in towns with sewerage systems and develop new infrastructure. | Increased sewerage connections in towns with sewerage systems and developed new in infrastructure ,including satellite sewerage systems in the Greater Metropolitan Area | i. New combined Faecal Sludge and Waste Water Treatment Plant of capacity 5000m3/day constructed at Old Port. ii. New Waste Water Treatment Plant of capacity 45,000m3/day constructed at Fishermens Point. iii. New Waste Water Treatment Plant of capacity 9,000m3/day constructed at Bad Shore. iv. Construction of mains sewers of a total length 30 km of varying sizes, ranging from DN 350mm to DN 1500mm linking catchment areas. | i. Old Port Faecal Sludge and Waste Water Treatment Plant was completed commissioned and is operational. ii. The construction of the Fishermens Point Waste Water Treatment Plant is at 88% completion. iii. Construction of the Bad Shore Waste Water Pre-treatment Plant is at 40% completion. iv. The construction of the main sewers is at 86% completion. | 295.4237 | 348.6 | 18% | 11.42% | 25.6 | 206.5 | 86.4 | 30.1 | 298.5 | 15.6 | 206.5 | 66.4 | 10 | 18 | 16 | 16.1 | 0 | 0 | 0 | 0 | 3.486 | 3.8153 | 4.1531 | 4.4823 | Yes | 272.9 | 280.2195 | 282.8094 | 285.9164 | 285.9164 | 285.9164 | 285.9164 | 292.9 | 0 | 7.3195 | 2.59 | 3.1069 | 0 | 0 | 0 | 6.9836 | 1 | 1 | 1 | 0 | 0 | 0
24 | Metropolitan Area Water Project | Water and Sanitation | National Water and Sewerage Corporation | GOP | Yes | NPV | 2168.2 | Ongoing | 10%-15% | Construct, operate and maintain piped water supply systems in small towns and urban areas country wide | Improve the socio-economic and health situation of the people living in the Metropolitan Area and hence further stimulate urban growth through provision of safe and reliable water supply. | i. Rehabilitated and upgraded two main Water Treatment Plants to capacity of 240 million liters. New transmission main pipes and new 8000m3 storage reservoir. ii. Hydraulic Model developed and updated GIS developed and operational. iii. Rehabilitated and restructured city center water supply network with sufficient carrying capacity to ensure reliable service delivery. iv. Development of new East Water Treatment Plant with its transmission, primary, secondary and tertiary pipe network and reservoirs to serve Eastern and Northern areas. | i. Rehabilitation and water production capacity optimization of Water Treatment Complex (plants 1 and 2) and transmission main pipes improvement is 95% complete. Construction of new the water reservoir tanks is 98% complete. Water Supply Extension is 50% completed and 1.100 new customers were connected. | 276.371 | 441.9 | 59.89% | 14.48% | 126.9 | 194.8 | 80.2 | 40 | 253.5841 | 17.766 | 155.8181 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 68.3159 | 4.419 | 4.8365 | 5.2646 | 5.6819 | Yes | 195.8181 | 203.9508 | 207.1883 | 211.0479 | 214.5618 | 220.307 | 227.7171 | 275 | 0 | 8.1327 | 3.2375 | 3.8595 | 3.514 | 5.7451 | 7.4102 | 47.2829 | 1 | 1 | 1 | 1 | 1 | 1
25 | Support to small town Water Supply Systems | Water and Sanitation | Ministry of Water and Sanitation | GOP | No | PVC/PVBenef | 1.3 | Ongoing | 81%-90% | Construct, operate and maintain piped water supply systems in small towns and urban areas country wide | Improved living conditions of people in small towns | 59 water supply systems countrywide rehabilitated and maintained. Opertion and maintenance manuals developed | Rehabilitation, expansion and extension of water supply systems and replacement of dysfunctional major electro-mechanical equipment which include pumps, motor control panels, chemical dossers, transformers, generators and water meters in at least 59 water supply systems countrywide. | 59.6154 | 64.5 | 8.194% | 2.113% | 15 | 19 | 20 | 10.5 | 29 | 0 | 16.9 | 4.6 | 7.5 | 24.3 | 5 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | 21.5 | 31.3813 | 32.1906 | 33.3871 | 33.3871 | 33.3871 | 33.3871 | 39 | 0 | 9.8813 | 0.80937 | 1.1965 | 0 | 0 | 0 | 5.6129 | 1 | 1 | 1 | 0 | 0 | 0
26 | Water for Production Center-East region | Water and Sanitation | Ministry of Water and Sanitation | GOP | Yes | NPV | 66.2 | New | 0% | Construct, operate and maintain piped water supply systems in small towns and urban areas country wide | Increased coverage and improved functionality of water for production facilities leading to improved quality of life of communities through increased house hold income. | a. Irrigation schemes, valley tanks and earth dams constructed or rehabilitated in the water stressed areas in Centre-East Pimnia. b. Water user committees or associations formed/revitalized on all the water for production facilities in Centre-East Pimnia. c. Districts staff have received capacity building and training programmes. | Identification and detailed design of various water for production facilities. Construction of irrigation schemes, valley tanks and earth dams in the water stressed areas. Formation, revitalization and training of water user committees or associations. | 30 | 30 | 0% | 0.983% | 12.3 | 0 | 10.7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 15.3 | 7 | 0 | 0 | 0.7 | 0.3 | 0.32834 | 0.35741 | 0.38574 | Yes | 0 | 0 | 1.1331 | 4.0857 | 5.3156 | 5.3156 | 5.3156 | 10.7 | 0 | 0 | 1.1331 | 2.9525 | 1.2299 | 0 | 0 | 5.3844 | 0 | 1 | 1 | 1 | 0 | 0
27 | Water for Production Center-North region | Water and Sanitation | Ministry of Water and Sanitation | GOP | No | NA | NA | New | 0% | Construct, operate and maintain piped water supply systems in small towns and urban areas country wide | Increased coverage and improved functionality of water for production facilities leading to improved quality of life of communities through increased house hold income. | a. Irrigation schemes, valley tanks and earth dams constructed or rehabilitated in the water stressed areas in Centre-North Pimnia. b. Water user committees or associations formed/revitalized on all the water for production facilities in Centre-North Pimnia. c. Districts staff have received capacity building and training programmes. | Identification and detailed design of various water for production facilities. Construction of irrigation schemes, valley tanks and earth dams in the water stressed areas. Formation, revitalization and training of water user committees or associations. | 29.85 | 29.85 | 0% | 0.9781% | 15.85 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15.85 | 0 | 0 | 0 | 0 | 0.2985 | 0.3267 | 0.35562 | 0.38381 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
28 | Water for Production Center-West region | Water and Sanitation | Ministry of Water and Sanitation | GOP | Yes | NPV | 101.1 | New | 0% | Construct, operate and maintain piped water supply systems in small towns and urban areas country wide | Increased coverage and improved functionality of water for production facilities leading to improved quality of life of communities through increased house hold income. | a. Irrigation schemes, valley tanks and earth dams constructed or rehabilitated in the water stressed areas in Centre-West Pimnia. b. Water user committees or associations formed/revitalized on all the water for production facilities in Centre-West Pimnia. c. Districts staff have received capacity building and training programmes. | Identification and detailed design of various water for production facilities. Construction of irrigation schemes, valley tanks and earth dams in the water stressed areas. Formation, revitalization and training of water user committees or associations | 29.75 | 29.75 | 0% | 0.9748% | 0 | 20 | 0 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2 | 15.35 | 7.2 | 0 | 0 | 0 | 0.2975 | 0.3256 | 0.35443 | 0.38252 | Yes | 0 | 0 | 1.1655 | 4.1277 | 5.3927 | 5.3927 | 5.3927 | 20 | 0 | 0 | 1.1655 | 2.9622 | 1.265 | 0 | 0 | 14.6073 | 0 | 1 | 1 | 1 | 0 | 0
[15 empty] | 975.711 |  | 31.97% | 149.483 | 550.569 | 238.029 | 37.63 | 0 | 0 | 0 | 0 | 0 | 0 | 140.83 | 229.96 | 292.71 | 172.86 | 119.14 | 20.211 | 21.4073 | 23.4296 | 25.5039 | 27.5254
[18 empty] | 4.898% | 18.04% | 7.799% | 1.233% | 0% | 0% | 0% | 0% | 0%
Note on G10: Rial, Isabel: Ministry of Health?

## Simulation of 2017 MTEF
| Total Project Cost | Previous Years | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer
MTEF Ceiling |  | 0 | 244.2 | 255.3416 | 285.1841 | 311.5572 | 342.2435 | 434.2674
Ongoing | 2350.8429 | 1386.9841 | 244.2 | 188.15 | 153.14 | 112.76 | 101.74 | 85.85
Agriculture | 35 | 30 | 3.4 | 1.6 | 0 | 0 | 0 | 0
Education | 41.5 | 23.7 | 10 | 6 | 1.8 | 0 | 0 | 0
Health | 126.5 | 82 | 15.5 | 10 | 7 | 7 | 5 | 0
Public Works and Transport | 1292.8429 | 670.2 | 153 | 129.55 | 102.04 | 85.76 | 76.74 | 65.85
Water and Sanitation | 855 | 581.0841 | 62.3 | 41 | 42.3 | 20 | 20 | 20
New | 541.371 | 0 | 0 | 61.4 | 134.45 | 185.57 | 82.64 | 57.1
Agriculture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Education | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Health | 34.57 | 0 | 0 | 8.2 | 12.4 | 10.37 | 0.9 | 0
Public Works and Transport | 447.051 | 0 | 0 | 39 | 91.4 | 161 | 81.74 | 57.1
Water and Sanitation | 59.75 | 0 | 0 | 14.2 | 30.65 | 14.2 | 0 | 0
Total | 2892.2139 | 1386.9841 | 244.2 | 249.55 | 287.59 | 298.33 | 184.38 | 142.95
Balance |  |  | 0 | 5.7916 | -2.4059 | 13.2272 | 157.8635 | 291.3174
|  |  |  | 2.268% | -0.8436% | 4.246% | 46.13% | 67.08%
| Total Project Cost | Previous Years | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Outer
Ongoing | 1521.0529 | 1116.7181 | 1195.7276 | 1221.0122 | 1247.5157 | 1265.9747 | 1295.2001 | 1327.0082 | 1521.0529
Agriculture | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Education | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Health | 95 | 80 | 86.3029 | 87.9216 | 89.2724 | 90.5023 | 91.9386 | 91.9386 | 95
Public Works and Transport | 786.1529 | 513.5 | 560.8732 | 577.9022 | 594.8919 | 608.6071 | 630.651 | 655.049 | 786.1529
Water and Sanitation | 606.9 | 490.2181 | 515.5516 | 522.1884 | 530.3513 | 533.8653 | 539.6104 | 547.0206 | 606.9
New | 439.358 | 0 | 0 | 9.939 | 35.8848 | 68.4893 | 92.2281 | 113.3842 | 439.358
Agriculture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Education | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Health | 20 | 0 | 0 | 1.3274 | 3.7203 | 5.5423 | 5.8008 | 5.8008 | 20
Public Works and Transport | 388.658 | 0 | 0 | 6.3131 | 23.9512 | 52.2388 | 75.719 | 96.8751 | 388.658
Water and Sanitation | 30.7 | 0 | 0 | 2.2986 | 8.2133 | 10.7083 | 10.7083 | 10.7083 | 30.7
Total | 1960.4109 | 1116.7181 | 1195.7276 | 1230.9512 | 1283.4005 | 1334.464 | 1387.4282 | 1440.3924 | 1960.4109
|  | 1276.8768 | 1355.8864 | 1391.11 | 1443.5592 | 1494.6228 | 1547.5869 | 1596.2736